## V.A.Birds
Retrospective: | Action point | Resp. | 1112 | 0201
Possible performance problems: If we have two days left, then try to run BEL or UC3 and find out its to slow; we have a problem. | : Run BEL or UC3 now, so we have an idea of the load and the speed. If longer than 5 hours, we have a problem. | TEAM
We should have a nightly build like save-as. (not only change-triggered build) | realize this in January. Johan takes care of this = making sure Timo can plan this in. Ask PO to make story for this. | SM
We need to have better contact with sales and marketing. If Sales and Marketing are pushing MN-R they should be present during the sprint-review. | : see if we can get this done. Contact Yves Muysens for this. | SM |  | done.
Post-gis loader; script all of a sudden becomes official software. | : always deny the existence of any non-official software. | TEAM
Combined-sprint review does not work; | : A sprint review separate per team, unless joint goals. Organize meetings separately | SM |  | postponed till next team setup
Sprint review presenters notified | Make sure next sprint review; persons that need to speak know this beforehand. | SM |  | done last sprint
Clarity in organisation: we need clarity on what the function of Timo, what the function of Siegfried is, what a "Program-manager" is, and we need to have this via mail. Also we still need an official communication that Lieven is now our line manager. | : We need to ask each of these persons to write a mail to answer these questions. * Program mgr, * Line mgr, * Timo function, *Siegfried function. | SM |  | Clarification follows on 7/01/2013
Sprint lenght. We need four weeks or maybe three week sprints to be efficient. | : Decide on sprint length, do the discussion with PO? | PO-TEAM
Clarity of stories: | make sure when we define a story, it is clearly defined. D.O.R. | PO-SM-TEAM
We need a definition of done for each story. | : SM will organize a meeting to make time for brainstorming on this. | SM-TEAM
We need a definition of ready: minimum requirements for a story from a product owner. Make this and pass this on to our product owner. Together with other teams or alone? | : Start with one in our teams and try to get other teams to join suit. | PO-SM-TEAM
Infrastructure: we need at least 2 and preferrably 4 network ports on the office, two network ports at jansonius, and a VM with a dns name "birds.tomtomgroup.com" on which we have root and where we can deploy sprint-reviews, e.g. postgress db, zoning-service software, start vagrant boxes, ... | request ports on desks | SM | Request 1-39754551 | done.
We need to focus: dependencies other team, other people. | : pay attention to this in the grooming & planning in order to determine if a story can start. | SM-TEAM |  | ongoing
Holidays, meetings, unplanned stuff: | : We need to take this into account during planning. | SM-TEAM |  | ongoing
Note on E4: Author: main reason for separation = separtion at customer side. It seems PM/PO's are customer oriented & only interested in the end product (which is not maps) So; the real customer is the customers Engineering dept. However they are only interested in the outcome at the due date. (Mainly due to lack of time, & the inferiour position of TomTom in automotive market. Is involvement at customers PM/PO level possible? (this would have an impact for the sprint review's format!)

## DAFPunk
Retrospective: | Action point | Resp. | 1112 | 0201
outcome and prospect 2013 | Ask Lieven vision on 2013 | SM |  | Monday 7/1/2013
knowledge share - Jan too less picked up | after work knowledge share sessions to go through developed work | TEAM
| manifest walk trough (dependency graph?) | TEAM
env failure Hardware/software/response... | create issue -> forward J // J-action after some time... | TEAM-SM |  | ???
puppet issue | better working of puppet but frontend: no dashboard splitting development/production | SM |  | done
Dev vs. Prod | better definition of done/process engineering -> all know how things are done | SM
cpp alignment | uniform cross departemental vision on automated deployment | SM |  | Monday 7/1/2013
| Stable ID story | SM- Stefan? |  | discussed w Timo, Timo will speak with Siegfried
individual tasks | better explain tasks and steps to take | TEAM
gezamelijke team blind spot | cross-functional alignment? Need for diversity Quality in teams.... Tackling this...? |  |  | Monday 7/1/2013 (new team setup could help?)
Team size | missing lander (note from PO: Landers knowledge should be shared @4/1/2013) Make place for knowledge transfer.

## Shebang
Retrospective: | Action point | Resp. | 1112 | 0201